## Questions and Answers
RFP 2026-1600-0027 - Offeror Questions and Answers from the State
Number | RFP Section | Question | Answer
1 | Section 3.07 - Contract Term and Work Schedule | This section indicates the system must go-live by July 1, 2026. Based on the projected contract issuance date set for November 2025 from section 1.11, that leaves an eight month or less duration to successfully complete the implementation. Is there any flexibility on this date? Typically, an IIS implementation may take from 12-15 months to successfully complete Alaska specific configurations, DOH testing, data migration, training, and re-establishing current data exchange connections. Less time requires committed support from Alaska DOH throughout the implementation, which may be challenging with other programmatic activities. It will also compress onboarding time for HL7 senders, reduce iterations for data migration and compresses training timelines for Alaska DOH and IIS users creating risks to quality and potentially system credibility with the immunization community. | Alaska DOH may allow flexibility on the go-live date if justified in the implementation plan.
2 | Section 2.02 - Background Information, Strenghths & Opportunities | The RFP lists the following item as an opportunity: “A connection to the state Health Information Exchange (HIE) could provide an opportunity for broader vaccine data access, especially to non-vaccinating health care providers.” Are there any known barriers to establishing a connection between VacTrAK and the state’s HIE? | There are no known technical barriers. The HIE provides access to payors, and Alaska’s Immunization Program charges HEDIS fees for immunization data access, as authorized under 7 AAC 27.655.
3 | Section 3.03 Deliverables, 6. Perform Data Migration, a. | Item 6a states: “The contractor will plan, code, extract, transform, load, test, and validate data conversion and migration processes.” We understand the current platform is a proprietary COTS product. To complete data migration as stated with minimal risk, this will require full access to the current production database, data dictionaries and SME support for questions not addressed in documentation. Are there any barriers to providing this access/support? If so, an alternative that has been successful is to have Alaska DOH, with any support needed from current vendor, extract the data placing it in prescribed file locations/format for the implementer to complete the remaining migrations steps. Would this approach be an acceptable alternative to propose? | The incumbent vendor is required to develop and submit a transition plan to facilitate a smooth transfer of the contracted functions to the new vendor or back to the division. DOH will be provided a full copy of VacTrAK Production Systems data. DOH would also be available to assist with database extracts as needed.
4 | Section 6.02 | Is an AK business license in order to submit our proposal? Could this be obtained later on if selected? | Please see RFP Section 6.02. An AK business license is not needed at time of proposal unless applying for the Alaska Bidder Preference and other related preferences. Yes, the selected contractor can obtain this later on prior to the award of the contract.
5 | Standard Agreement Form | We were not able to locate exhibits denoted in Article 2 on the Standard Agreement Form. We are specifically looking for Appendix B, C, D and E. Can you please provide those? | The standard agreement form is an example of the contract as a result from the RFP. Appendix B is 3.21 (idemnification and insurance requirements). Appendix C will outline the scope of work, SLA, and deliverables from section 3.01 - 3.03. Appendix D will outline the payment process and incorporate the awarded vendor's cost proposal. Appendix E is Attachment 6.
6 | Section 3.03-3.05 | Do we need to respond to the NIST questions as part of our proposal submission? | No. Per the first page of the NIST Questionnaire document, these are for reference only and should not be answered with proposal submission. This document is just to assist your firm in determining the level of effort that may be required for this deliverable. See section 3.03, #1 and 3.04 of the RFP.
7 | Section 3.03-3.05 | If we have already completed the NIST questionnaire on a separate Alaska contract, do we have to do it again for this project? | Yes, if awarded the contract, the vendor will still need to go through the process as outlined in the RFP.
8 | General | Does the State require a specific file naming convention for Technical and Cost Proposal, or is this left to the Offeror? | There is no file naming convention required. See section 1.07 - Return Instructions.
9 | Section 3.05, Business Associate Agreement & Information Security Agreement | Please confirm whether the State will accept redlined versions of these agreements as part of the RFP Response package, or if acknowledgment of compliance is sufficient at this stage. | See Section 6.04. If any offeror has any changes to Section 1 of the document, it can be done as redlines and must be submitted with the offeror's proposal as a seperate document. No changes/redlines are allowed in section 2 - ISA.
10 | Section 3.05, Business Associate Agreement & Information Security Agreement | Please confirm whether Offerors are allowed to take exceptions to the Business Associate Agreement (BAA) and Information Sharing Agreement (ISA)? Specifically, will the State accept exceptions to these agreements as part of the RFP response? | See Section 6.04. If any offeror has any changes to Section 1 of the document, it can be done as redlines and must be submitted with the offeror's proposal as a seperate document. No changes/redlines are allowed in section 2 - ISA.
11 | Appendix A, Standard Contract Provisions | Please confirm whether the State will accept redlined versions of Appendix A as part of the RFP Response package, or if acceptance is assumed unless exceptions are identified. | See Section 6.03. Any requests to change the langauge in this document must be set out in the offeror's proposal as a separate document. Failure to provide this will be considered acceptance.
12 | RFP Section 4.03 – Submittal Form A (Offeror Information and Certifications) | Can the State please clarify whether it is acceptable for Offerors to sign (full signature) in the initials fields, instead of providing abbreviated initials, as long as the authorized representative’s signature is also provided at the end of the form? | Yes.
13 | RFP Section 1.11 – RFP Schedule | Given that questions are due September 14 and proposals are due September 24, leaving limited time to incorporate State responses, would the State consider extending the proposal due date by two weeks? | Questions being due 10 days before the deadline for reciept of proposal is the states standard practice. We do not anticipate extending the deadline at this time.
14 | RFP Section 4.02 – Special Formatting Requirements | Given the page limitations, may Offerors include product user workflow descriptions and screenshots in a separate appendix that does not count toward the page limits of the main proposal? | No, offerors must provide all information within the submittal form page limits. Any additional documents/appendices submitted will not be reviewed/evaluated by the PEC.
15 | RFP Section 3.03 – Deliverables: Data Conversion and Migration Roadmap | Can the State clarify expectations for historical immunization data migration—does the vendor need to migrate all 17M+ historical doses from VacTrAK, or only a defined lookback period (e.g., last 10 years)? | We would anticipate all doses currently in VacTrAK to be migrated. However, we do not necessarily expect all associated administration details to be migrated for every dose. At a minimum, the migrated data should include all available statue required fields (7 AAC 27.650) for administerd vaccines beginning in 2014. For records prior to 2014, prior to the VacTrAK reporting requirement, we are open to migrating a more limited set of fields. The final determination of of what data are migrated can take into account vendor recommendations.
16 | RFP Section 3.01 – Scope of Work | The RFP requires compliance with CDC/ONC Data Quality Certification “once available.” Can the State clarify if it expects the Offeror to build a flexible compliance framework now (anticipating evolving certification requirements), or simply adapt once standards are finalized? | See RFP Amendment 3, Change 2. The offeror should provide details on how they will adapt once standards are finalized. See also Section 3.18 - Contract Changes - Anticipated Amendment.
17 | RFP Section 3.03 – Deliverables: Data Conversion and Migration Roadmap | Can the state please provide the following information for the current database? Current Data Volume and Growth Rate: • Total size of the data to be migrated from the source system. • Estimate the expected data growth rate within the SaaS environment to project future storage needs. • Historical data trends and anticipated user adoption or feature expansion that might impact data volume. | Our registry database is over 600 GB, and our interface database is over 1300 GB. This excludes tables from non-production environments. The actual volume of data to be migrated is expected to be less, depending on the selection of core tables (patients, vaccinations, provider configution, and vaccine configuragation) and the migration strategy developed in collaboration with the selected offeror. Actual storage growth will depend on the selected offeror’s data model, auditing and logging practices, and any additional services implemented. Below is a summary of Alaska’s estimated annual growth: Patients: ~30,000 Vaccination Events: ~500,000 (administered and historical) User Accounts: ~1,500 Organizations: ~20 Facilities: ~60 Feature expansion will depend on CDC/ONC Data Quality Certification, including alignment with the CDC’s Requirements Traceability Matrix (RTM) and updates to the Functional Standards and Data Quality Blueprint. Potential areas of expansion may include: Implementation of FHIR-based services CDSi changes and enhancements Additional data domains (e.g., exemptions and refusals, contraindications and precautions, maternal-child record linkage) Increased exchange with EHRs, HIEs, and IZ Gateway Integrated data analytics and visualization Onboarding modules not currently in use (e.g., school/childcare, Perinatal Hep B, etc.)
19 | RFP 2026-1600-0027 - Submittal Form H (RTM) ( Functional Requirements TAB) | Could the State please provide clarification on the instructions for completing the RTM, specifically for: Column F: Similar Functionality Column G: Configuration Required Column H: Modification Required Column I: Future Release For example, if a vendor marks Column E – Out of the Box Functionality, are we also required to complete Columns F through I, or should those remain blank? | See RFP Amendment 3, Change 3. Offerors should only select one column.
20 | RFP 2026-1600-0027 - Submittal Form H (RTM) (Technical Requirements TAB) | Please clarify the instructions for completing the RTM. Specifically, if an Offeror selects Column E – Out of the Box Functionality, should the Offeror also select Column G – Configuration Required or Column H – Modification Required, or should those columns remain blank? In other words, should the Offeror select only one of these columns, or may multiple columns be selected for a single requirement? | See RFP Amendment 3, Change 3. Offerors should only select one column.
21 | General | Considering incumbent will not incur any DDI/Implementation cost, could the state exclude DDI cost from the cost evaluation? | No, it is within the states best interest to evaluate all costs associated with the requirements of this RFP. The RFP already has a lowered cost evaluation weight.
22 | Submittal Form I - IT-Related Contractual Requirements | Please confirm if the dropdown requirements in Submittal Form I – Column F “Response Column” are intentionally different across requirement IDs? For example, the dropdown options for Req ID IT3 differ from those for Req ID IT4. | This is intentional.
23 | Section 3.03 Deliverables No. 18 Customer Support Services | Will DOH provide access to DOH ticketing system for Tier 2 Contractor support staff? Can DOH provide the volume of Tier 2 tickets by contact type (call, email, etc.) during workday hours 8 to 5pm and afterhours. | We are not currently able to provide access to contractor support staff, but will explore options in shared ticketing with selected offeror. Tier 2 support calls are rare, with one or fewer per month. Email volume is on average 30 per month. We anticipage a higher volume for system transitions. Calls and emails are not expected to be responded to end users outside of normal business hours.
24 | Section 3.03 Deliverables No. 11 Conduct Training c) | Please provide the number of anticipated participants referred to in the following sentence from the RFP: "System users (end users) for comprehensive training 90 days prior to implementation to plan for the number of sessions that need to be completed?" | We expect all active users to participate in some level of training prior to implementation. Training may be self-directed for most users, but live training would likely be required for organization and facility administrators and users with inventory management permissions. Based on current active user data: View-only users – 1,367 (minimal training); View/edit users – 2,613 (self-directed or guided training); 428 non-registry users with ordering permissions (live training required); and 20 registry clients (trained early).
25 | RFP 2026-1600-0027 - Submittal Form H (RTM) ( Technical Requirements TAB) | The Instructions tab states that the Offeror must mark the column that applies to the system for each row with an "X." However, the Technical Requirements tab does not appear to provide an option to enter an "X" in any of the rows. Could the State please issue a revised Excel file that allows Offerors to mark the applicable responses as instructed? | See RFP Amendment 3, Change 3.
26 | RFP 2026-1600-0027 - Submittal Form H (RTM) ( Technical Requirements TAB) | Could the State please clarify what is meant by the “Similar Functionality” column in the Technical Requirements tab? | See RFP Amendment 3, Change 3.
27 | Section 3.12 Subcontractors | Should Offerors consider affiliates as a Subcontractor for Submittal Form G - Subcontractors? | Any other company aside from the prime contractor providing services on this contract is considered a subcontractor.
28 | General | "The length of the contract will be from contract start, until June 30, 2027 with nine (9) one-year renewals at the sole discretion of the stated. The system must go live by July 1, 2026." Based on this extract in the RFP, total term is more than 10 years. cost proposal only includes 10 years to represents pricing. Could the State please update the price sheet that allows us to input 10 years and 8 months of pricing assuming a Nov 2025 start date? | See RFP Amendment 3, Change 1. Contract term will only be for ten (10) years total.
32 | Section 6.04 HIPAA BAA & ISA | The ISA prohibits offshoring of PHI. Does this restriction apply equally to development staff who may work offshore without accessing PHI, or only to environments where PHI is stored/processed? | The ISA is prohibiting offshoring without prior written approval. By signing their proposal, offerors are certifying that all work will be performed in the United States. If an offeror cannot certify this, they must submit a request with their proposal in a separate document. See RFP Section 3.11 - Location of Work.
33 | Section 3.07 Contract Term and Work Schedule | Go-live is set for July 1, 2026. Will the State consider proposals that deliver in phased rollouts (registry first, inventory second) as long as full compliance is achieved by the deadline? | Yes.
34 | Submittal Form I - IT-Related Contractual Requirements | There seems to be an inconsistency between RFP Section 3.02, which states 99.99% availability and Submittal Form I: IT-Related Contractual Requirements, IT28, which states 99.999%. Which is the correct requirement? | The RFP SLA requirement of 99.99%. The IT-Related Contractual Requirements is only asking the offeror to attest to what availability they can provide.
35 | Section 3.01 Scope of Work - Vaccine Ordering and Management System (VOMS) | Does the State require full compliance with CDC’s VTrckS ordering interface at go-live, or will phased compliance (post go-live) be acceptable? | Phased compliance is acceptable; however, at the time of go-live, the system must be capable of generating accurate files for Provider Master Data, Provider Inventory Data, Provider Order Data, and Vaccine Returns Data in accordance with the VTrckS ExIS specification. Additionally, the system must support the import of shipment data files from VTrckS at go-live.
36 | Section 3.03 Deliverables - Data Migration | Will the State provide data dictionaries and schema documentation for the incumbent vendor’s system (STChealth), and will the incumbent be contractually required to cooperate with data migration? | The current IIS database structure, schema, and data dictionaries are proprietary and cannot be shared at this time. Yes, the incumbent vendor is contractually required to provide a smooth transfer of the contracted functions to the new vendor or back to the state.
37 | Section 3.03 Deliverables - Training | Can the State confirm expected training audience size (e.g., number of providers, DOH staff, school nurses) to ensure appropriate scaling of training resources? | See Q&A #24 above.
38 | Submittal Form H (RTM) | Per the instructions - 'If function is not included as "Out of the Box", offerors should complete the comment section to include timeline for development and release.' Does that apply to requirements that are marked as 'Similar Function' or does it only apply to the other categories - Configuration Required, Modification or Future Release? According to your definition of 'Similar Function', the Offeror's system offers similar functionality that can meet the needs of the requirement. Please clarify. | If the similar function is not out of the box, offerors should complete the comment section to include timeline for development and release.
39 | General | Should the Standard Agreement Form for Professional Services be included with the proposal? | No, only Appendix A needs to be submitted if the offeror takes exception to the Terms and Conditions (see Q&A #11).
40 | General | Can letters of support be submitted as a separate attachment? | No, offerors must provide all information within the submittal form page limits. Any additional documents/appendices submitted will not be reviewed/evaluated by the PEC.