State of Alaska

Department of Natural Resources

Division of Mining, Land and Water

Application for Easement

Tanana Chiefs Conference

The Tanana Chiefs Conference (TCC) has been awarded ReConnect Grant AK1708-A73 by the US Department of Agriculture (USDA) Rural Utilities Service (RUS) to create infrastructure to provide high-speed internet to the following four Koyukuk River communities in rural interior Alaska: Hughes, Allakaket, Alatna, and Evansville.

Broadband internet will provide residents the ability to earn income, meet with health care providers, shop, receive job training virtually, and fully participate in local land use planning decisions that require the ability to download large documents and submit comments online.

The full project will consist of two main components: 171.78 linear miles of mainline fiber between communities and fiber to the home in each of the four communities. In total, 39.77 miles of fiber will cross State lands.

Plans for Initial Construction

Global Positioning System (GPS) coordinates will be used to locate the fiber centerline, and it will be flagged by personnel.

The alignment will primarily be ground-laid, aside from where the engineers have recommended Horizontal Directional Drilling (beneath waterbodies) and burial (in high-traffic areas near communities). Areas that require clearing have been avoided to the extent possible through route design, however, clearing will occur within the 20-foot-wide construction corridor to allow for equipment to pass through. Vegetation will be cut at the ground surface, allowing the root base to be left intact. Cleared vegetation will be masticated. To reduce potential for avian impact during construction, clearing and trenched installation of mainline fiber will occur outside of the U.S. Fish and Wildlife Service’s Land Clearing Timing Guidance for Alaska - Recommended Time Period to Avoid Vegetation Clearing. Per this guidance, vegetation clearing will not occur from May 1 – July 15.

The construction corridor will be flagged and cleared ahead of a mobile construction unit, which will follow to install the fiber. Where fiber will be buried, it will be installed in a six-inch-wide trench, one-foot in depth.

The shallow burial proposed is intended to minimize ground-disturbance, erosion, and changes to surficial water flow by preserving the vegetative mat and underlying soil. The goal is to place fiber just under the vegetative mat. Materials excavated will be placed back into the trench with the fiber, and the vegetative mat will be placed on top.

Please see the description below of where fiber will be buried, ground-laid, and bored. Please note that this summary excludes 24.17 miles of fiber that are within the communities.

Miles 0 – 1.5 		Buried

Mile 1.5		Jim River HDD Bore

Mile 1.5 – 13.7 	On Ground

Mile 13.7 – 13.8	South Fork Koyukuk HDD Bore

Mile 13.8 – 26.3	On Ground

Mile 26.3 – 26.9	Buried

Mile 26.9 – 32		On Ground

Mile 32 – 32.2		Koyukuk River HDD Bore

Mile 32.2 – 68.6	On Ground

Mile 68.6 – 68.8	Alatna River HDD Bore

Mile 68.8 -73.4	On Ground

Mile 73.4 – 73.6	Existing Koyukuk River HDD Bore

Mile 73.6 - 74.6	Buried

Mile 74.6 – 92.4	On Ground

Mile 92.4 – 92.5	Kanuti River HDD Bore

Mile 92.5 – 142.7 	On Ground

Mile 142.7 – 147.3	Buried

Legal Description

MTRS of State Land Crossings

| Township | Range | Section |
| --- | --- | --- |
| 23N | 14W | 30 |
| 23N | 15W | 25 |
| 23N | 15W | 26 |
| 23N | 15W | 23 |
| 23N | 15W | 22 |
| 23N | 15W | 21 |
| 23N | 15W | 28 |
| 23N | 15W | 29 |
| 23N | 15W | 30 |
| 23N | 16W | 25 |
| 23N | 16W | 26 |
| 23N | 16W | 27 |
| 23N | 16W | 22 |
| 23N | 16W | 15 |
| 23N | 16W | 16 |
| 23N | 16W | 9 |
| 23N | 16W | 8 |
| 23N | 16W | 5 |
| 23N | 16W | 6 |
| 24N | 17W | 19 |
| 24N | 21W | 36 |
| 24N | 21W | 35 |
| 24N | 21W | 34 |
| 24N | 21W | 33 |
| 23N | 21W | 4 |
| 23N | 21W | 5 |
| 23N | 21W | 8 |
| 23N | 21W | 7 |
| 23N | 22W | 12 |
| 23N | 22W | 13 |
| 23N | 22W | 14 |
| 23N | 22W | 15 |
| 23N | 22W | 16 |
| 23N | 22W | 21 |
| 23N | 22W | 28 |
| 23N | 22W | 29 |
| 23N | 22W | 32 |
| 23N | 22W | 31 |
| 23N | 23W | 36 |
| 22N | 23W | 2 |
| 22N | 23W | 11 |
| 22N | 23W | 14 |
| 22N | 23W | 23 |
| 22N | 23W | 22 |
| 22N | 23W | 27 |
| 22N | 23W | 34 |
| 8N | 25E | 7 |
| 8N | 25E | 6 |
| 8N | 25E | 5 |
| 7N | 22E | 3 |
| 7N | 22E | 10 |
| 7N | 22E | 11 |

Sections of Alignment Crossing State Land

| Start Coordinates | End Coordinates | Length in Miles |
| --- | --- | --- |
| 66.03204076, -154.2284235 | 66.02287433, -154.1574305 | 2.20 |
| 66.10655174, -153.700198 | 66.12161668, -153.6317703 | 2.28 |
| 66.68192671, -152.5196318 | 66.75936478, -152.4702703 | 5.56 |
| 66.76850363, -152.448093 | 66.85557705, -151.9982398 | 14.40 |
| 66.8881921, -151.3449957 | 66.88398586, -151.3272829 | 0.57 |
| 66.85372091, -151.1272423 | 66.84673345, -151.098903 | 0.99 |
| 66.84680655, -151.0969079 | 66.79372646 -150.7328556 | 12.23 |
| 66.79390568, -150.7317459 | 66.78842186 -150.6882977 | 1.54 |

Terrain

The project area is south of the Brooks Range in an area dominated by black spruce and intersected by several braided streams and rivers. Elevation along the route ranges from a low of approximately 300 feet in Hughes to a high of 2,500 feet on the stretch between Hughes and Allakaket.

Fiber will be installed in a six-inch-wide trench, one-foot in depth. The shallow burial proposed is intended to minimize ground-disturbance, erosion, and changes to surficial water flow by preserving the vegetative mat and underlying soil. The goal is to place fiber just under the vegetative mat. Materials excavated will be placed back into the trench with the fiber, and the vegetative mat will be placed on top.

Access

During construction, the site will be accessed via snowmachine from the project communities. Other vehicles that will be used onsite include a D6 size bulldozer, mini excavator, snow groomer, bore machine, and chain trencher. If the site needs to be accessed for maintenance post-construction, snowmachines will be used in the winter and a helicopter during the summer.

Buildings

No permanent buildings will be onsite, however, an 8x20’ container-style camp on skis will be towed along and used during construction.

Power Source

Two to three 4500w generators will be used as a power source during construction.

Waste

All waste will be hauled out or disposed of in a landfill at one of the communities along the project route. Waste will be disposed of properly and in accordance with local and state law.

Hazardous Substances

No hazardous substances will be generated or stored onsite, other than fuel for vehicles and equipment. No more than 800 gallons of fuel will be stored at any time.

Water Supply

Water will not be required for construction purposes. Drinking water for the construction crew will be transported with the portable camp building.

Parking and Storage

Any extra vehicles or equipment will be stored in the communities at the central office site.

Site Use

Twelve to fourteen personnel will be onsite at any given time. The supervisor to staff ratio will be 1:6.

Maintenance and Operations

A subcontractor will be secured for the purpose of emergency maintenance, which will be done by helicopter or snowmachine. No routine maintenance will be required.

Closure Plan

Termination of the right-of-way will occur when the fiber is no longer useable or replaced by advanced technology, more than 30 years into the future. Leaving fiber in-place, with vegetation growing over the trench, is the preferred action for rehabilitating federal lands. Locating the fiber cable and removing it from under the vegetative mat will cause additional damage of federal lands and potentially localized erosion.